## Sheet1
ID | Regression Testing checklist | Estmation Time(Com) | Estmation Time(BOS) | com est | Bos Est
1 | Registration | Can't Automate (captcha) | Can't Automate (captcha) | 0 | 8
2 | Login | Can't Automate (captcha) | Can't Automate (captcha) | 0 | 4 | 240 | hrs
3 | Login with all social media | Can't Automate (captcha) | Can't Automate (captcha) | 0 | 4
4 | Search functionality | 8 hour | 8 hour | 8 | 8
5 | Home page | 20 hour | 20 hour | 20 | 20
6 | Home page popup | 2hour | 2hour | 2 | 2
7 | Dealer price | q | q | 7 | 7
8 | Product Detail page (Random) | 4 hour | 4 hour | 4 | 4
9 | Option dropdown available on product detail page work properly or not? | 16 hour | 16 hour | 16 | 16
10 | Total Price on product detail page upadate according to option selection or not? | 8 hour | 8 hour | 8 | 8
11 | Size conversation works or not | 8 hour | 8 hour | 8 | 8
12 | Price update with Qty or not | 4 hour | 4 hour | 4 | 4
13 | Templates on product detail | 4 hour | 4 hour | 4 | 4
14 | Upload Art work | 8hour | 8hour | 8 | 8
15 | Design Tool | 12hour | 12hour | 12 | 12
16 | Size Drop down and price reflection on Design Tool | 12hour | 12hour | 12 | 12
17 | Review page of Design Tool | 8hour | 8hour | 8 | 8
18 | Category page (Random) | 8hour | 8hour | 8 | 8
19 | Filter functionality on category pages | Q | Q | 6 | 6
20 | Sorting on category pages | Q | Q | 6 | 6
21 | Cart page | Q | Q | 6 | 6
22 | Checkout page | Q | Q | 6 | 6
23 | Order Cycle with paypal | 8 hour | 8 hour | 8 | 8
24 | Order Cycle with credit Card | 8 hour | 8 hour | 8 | 8
25 | Order Cycle with Amazon | 8 hour | 8 hour | 8 | 8
26 | Order Data--my Account | Q | Q | 6 | 6
27 | Address book verification | Q | Q | 6 | 6
28 | Vector order | Q | Q | 1 | 1
29 | Payment from My Account | Can't Automate (captcha) | Can't Automate (captcha) | 16 | 16
30 | Reorder | Can't Automate (captcha) | Can't Automate (captcha) | 8 | 8
[6 empty] | Total | 444hrs
[6 empty] | Effort reduced due to Reusable methods(20% of Total) | 89hrs
[6 empty] | Grand Total | 355hrs | in days | 44.375 | 45days